CALL SHEET — Scene 12 Test Shoot

Film: Mysterious Guest (میوانێکی نادیار)

Director: Sarwar Muhedin

Production: [Company Name TBD]

Date: [TBD]

Day: 1 of 1 (Single Scene Test Shoot)

Weather: Interior — Not Weather Dependent

Call Sheet Issued By: [AD Name TBD]

General Information

| Field | Detail |
| --- | --- |
| Shooting Location | Garden House Interior [Full Address TBD] |
| Nearest Hospital | [TBD — identify on location scout] |
| Nearest Pharmacy | [TBD] |
| Location Contact | [Property Owner Name + Phone TBD] |
| Parking | [TBD — confirm on scout] |
| Craft Services | On-site — porch or separate room [confirm on scout] |
| Sunrise | [TBD — check for date] |
| Sunset | [TBD — not critical for interior but useful for exterior ambience] |

Schedule Overview

| Time | Activity |
| --- | --- |
| [T-60 min] | CREW CALL. Unload equipment. Begin set dressing. |
| [T-45 min] | Gaffer begins lighting setup. |
| [T-20 min] | CAST CALL. Wardrobe + makeup check. |
| [T-15 min] | Blocking rehearsal — Shot 12.1 with actors on track. |
| [T-5 min] | Final checks: frame, focus, sound, slate. |
| [T+0:00] | FIRST TAKE — Block 1 (Shot 12.1, Tracking) |
| [T+0:45] | Block 2 (Shots 12.6, 12.3) |
| [T+1:20] | Block 3 (Shot 12.4) |
| [T+1:30] | BREAK 1 (15 min) |
| [T+1:45] | Block 4 (Shots 12.10, 12.12) |
| [T+2:00] | Block 5 (Shots 12.7, 12.9, 12.8) |
| [T+2:20] | Block 6 (Shot 12.5) |
| [T+2:35] | Block 7 (Shot 12.11) |
| [T+2:50] | BREAK 2 (15 min) |
| [T+3:05] | Block 8 (Shot 12.13) |
| [T+3:20] | Block 9 (Shot 12.2) |
| [T+3:30] | Block 10 (Shot 12.14) |
| [T+3:50] | Block 11 (Shot 12.15) |
| [T+4:00] | Wild sound recording. |
| [T+4:20] | WRAP. Strike set. Backup footage + audio. |
| [T+5:00] | ALL CLEAR. Location restored. |

Cast

| # | Character | Actor | Call Time | Wardrobe | Makeup | On Set | First Shot | Last Shot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Nali | [TBD] | T-20 | Linen olive/sage | Minimal | T-5 | 12.1 | 12.15 |
| 2 | Gesha | [TBD] | T-20 | Dark top/pants | No-makeup | T-5 | 12.1 | 12.14 |

Notes:

Gesha wraps after Block 10. Nali has rest during Blocks 6 and 9. Both remain on set for off-screen eyelines.

Crew

| Role | Name | Phone | Call Time | Notes |
| --- | --- | --- | --- | --- |
| Director | Sarwar Muhedin | [TBD] | T-60 min |  |
| 1st AD | [TBD] | [TBD] | T-60 min | Manages schedule |
| DP / Cinematographer | [TBD] | [TBD] | T-60 min |  |
| 1st AC / Focus Puller | [TBD] | [TBD] | T-60 min |  |
| Gaffer | [TBD] | [TBD] | T-60 min |  |
| Grip | [TBD] | [TBD] | T-60 min | Dolly operation |
| Sound Mixer | [TBD] | [TBD] | T-60 min |  |
| Boom Operator | [TBD] | [TBD] | T-60 min |  |
| Script Supervisor | [TBD] | [TBD] | T-20 min | Continuity notes |
| Props Master | [TBD] | [TBD] | T-90 min | Early for set dressing |
| Wardrobe | [TBD] | [TBD] | T-30 min | Cast call |
| Makeup / Hair | [TBD] | [TBD] | T-30 min | Cast call |
| Production Assistant | [TBD] | [TBD] | T-60 min | General support |

Minimum crew: 8 (Director, DP, Gaffer, Grip, Sound, Script Sup, 1 PA).

Equipment Manifest

| Category | Items | Responsible |
| --- | --- | --- |
| Camera | Primary body + backup, monitor | DP |
| Lenses | 18mm to 85mm prime set | DP / 1st AC |
| Support | Tripod, dolly + 3m track, slider | Grip |
| Lighting | 2× LED panels, fresnel, dimmers, bulbs, gels | Gaffer |
| Grip | 3× C-stands, bounce, flags, sandbags | Grip |
| Sound | Recorder, boom + shotgun, 2× wireless lavs | Sound Mixer |
| Video Village | Monitor, table, chairs | PA |
| Misc | Slate, tape, focus marks, cables | PA / 1st AC |

Meals & Craft Services

| Item | Time | Notes |
| --- | --- | --- |
| Craft Services | T-60 min onward | Water, coffee, juice, fruit, biscuits. Outside room. |
| Lunch / Main Meal | During Break 2 [T+2:50] | Sandwiches, wraps. Vegetarian option. |
| End-of-Day | After wrap | Thank-you tea/coffee. Optional. |

Emergency Contacts

| Contact | Name | Phone |
| --- | --- | --- |
| Production Manager | [TBD] | [TBD] |
| Director | Sarwar Muhedin | [TBD] |
| Nearest Hospital | [TBD] | [TBD] |
| Location Owner | [TBD] | [TBD] |
| Police (local) | [TBD] | [TBD] |

Important Notes

1. PHONES ON SILENT. No exceptions. A ringing phone during the locked door take will cost 10 minutes.

2. NO SMOKING inside the location. Smoke lingers and affects continuity and actors's breathing.

3. QUIET ON SET discipline is critical. 7 of 15 shots have dialogue. The boom is always hot.

4. CONTINUITY PHOTOS by script supervisor before Block 1 and after adjustments. Both actors: front, profiles, full body.

5. FOOTAGE BACKUP during final 20 minutes. All cards and audio to TWO drives before anyone leaves.

6. LOCATION RESPECT. Leave it as found. Unmount wall items, fill holes if possible. Collect crew trash.

Document Status: TEMPLATE v1.0 — April 2026 Fill in [TBD] fields when cast, crew, date, and location are confirmed.