RISK & CONTINGENCY NOTES — Scene 12

Film: Mysterious Guest (میوانێکی نادیار)

Director: Sarwar Muhedin

Scene: 12 — INT. Garden House — Evening

Status: LOCKED v1.0

Risk Assessment Overview

Scene 12 is an interior shoot with controlled conditions, lowering overall risk. Primary risks: time overrun on complex setups, prop sourcing failures, equipment malfunction, actor performance. Each risk is rated with specific contingency.

CATEGORY 1: Time & Schedule Risks

Risk 1.1 — Tracking Shot (12.1) Eats Schedule

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | HIGH |  |
| Impact | HIGH |  |
| Description | Shot 12.1 is complex: dolly 3m, pan, hold, blocking. Each cycle ~4 min. 8 takes = 32 min rolling + rehearsal. |  |
| Contingency | Hard cap at take 8. If no clean take, split into: (A) Wide static entering, (B) Medium on Gesha reaction. |  |
| Prevention | 15 min blocking rehearsal. Walk dolly path 3×. Mark focus points, pan stop, position with tape. |  |

Risk 1.2 — Dialogue Shots Run Long

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | MEDIUM |  |
| Impact | MEDIUM |  |
| Description | 7 shots have dialogue. More takes needed than silent shots. |  |
| Contingency | Sacrificial shot: 12.2 (room reveal). Beautiful but no actors/dialogue. Cut to 1 take or drop entirely. |  |
| Prevention | Print dialogue sides day before. Run lines during Blocks 6 and 9 (actor-free). |  |

Risk 1.3 — Director Wants More Coverage

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | MEDIUM |  |
| Impact | MEDIUM–HIGH |  |
| Description | Director may request additional angles not in locked breakdown. |  |
| Contingency | AD tracks time publicly. If director requests shots, AD presents trade: "This costs Block 9 or wild sound." |  |
| Prevention | Review shot list with director day before. Confirm 15 shots settled before shoot day. |  |

CATEGORY 2: Equipment Risks

Risk 2.1 — Dolly/Track Failure

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | LOW |  |
| Impact | HIGH | Affects Shots 12.1, 12.5, 12.11 |
| Description | Dolly wheel jam, track misalignment, uneven floor. |  |
| Contingency | Steadicam fallback for 12.1. Handheld (changes aesthetic). Slider for 12.5 and 12.11. |  |
| Prevention | Test dolly on location floor day before. Shims for leveling. Backup slider. |  |

Risk 2.2 — Camera or Lens Failure

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | LOW |  |
| Impact | CRITICAL |  |
| Description | Sensor malfunction, card failure, lens damage. |  |
| Contingency | Backup camera body. Most-used lens: 50mm (6 shots) — if fails, 40mm substitutes. Protect 85mm. |  |
| Prevention | Camera and lenses checked day before. Cards formatted. Minimum 2 cards, rotate. Lens caps on. |  |

Risk 2.3 — Lighting Equipment Failure

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | LOW–MEDIUM |  |
| Impact | MEDIUM |  |
| Description | LED panel failure, dimmer malfunction, bulb blowout. |  |
| Contingency | Spare bulbs (warm 2700K). If LED fails, rearrange panel. Dedolight replaceable with phone flashlight + CTO gel. |  |
| Prevention | Power all lighting day before. Backup dimmers. Label cables and connections. |  |

Risk 2.4 — Sound Equipment Failure

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | LOW |  |
| Impact | HIGH (7 dialogue shots) |  |
| Description | Wireless lav interference, boom cable failure, recorder malfunction. |  |
| Contingency | Camera scratch audio backup. If one lav fails, remaining lav + boom sufficient. Never shoot dialogue without audio. |  |
| Prevention | Fresh batteries in transmitters. Backup batteries on set. RF interference scan at scout. Test cables day before. |  |

CATEGORY 3: Prop & Set Risks

Risk 3.1 — Deer Head Not Available

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | MEDIUM | Depends on local sourcing |
| Impact | HIGH | 6 shots, referenced in dialogue |
| Description | Realistic taxidermy difficult to source on short notice. |  |
| Contingency | Tier 1: High-quality replica (2+ weeks). Tier 2: Painting/photo in frame. Tier 3: Different animal (boar, ram). |  |
| Prevention | Start sourcing IMMEDIATELY. Hunters, antique dealers, theater houses, taxidermists. Local buy/sell groups. |  |

Risk 3.2 — Deer Head Falls During Shooting

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | LOW | If properly mounted |
| Impact | CRITICAL | Safety hazard + damage + lost time |
| Description | Taxidermy head is heavy (5–10 kg). Wall mount failure causes fall. |  |
| Contingency | STOP. Check injuries. Assess damage. If repairable, remount. If destroyed, switch to Tier 2. |  |
| Prevention | Test mount under load day before. Toggle bolts/masonry anchors. SAFETY WIRE from back to second anchor. |  |

Risk 3.3 — Locked Door Doesn't Lock Convincingly

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | MEDIUM |  |
| Impact | MEDIUM | 12.14 depends on lock feeling genuine |
| Description | Door lacks functioning lock or handle doesn't communicate "locked" on camera/sound. |  |
| Contingency | Install simple deadbolt or sliding bolt before shoot. Rubber door stop wedged from far side. |  |
| Prevention | Test on scout day. Does handle rattle? Door give then stop? SOUNDS locked? Install hardware if needed. |  |

CATEGORY 4: Actor & Performance Risks

Risk 4.1 — Actors Not Cast in Time

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | MEDIUM | Compressed timeline |
| Impact | CRITICAL | No actors = no shoot |
| Description | Director hasn't finalized casting for Nali and Gesha. |  |
| Contingency | Casting deadline 1 week before shoot. Postpone if deadline missed. |  |
| Prevention | Include casting status in every meeting. Provide breakdowns, organize audition, review tapes. |  |

Risk 4.2 — Actor Fatigue

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | MEDIUM |  |
| Impact | MEDIUM–HIGH |  |
| Description | 5 hours of one scene. Dialogue requires range. Emotional drain by Block 10. |  |
| Contingency | Call unscheduled 10-min break. Director speaks to actress privately (reset). Series of shorter takes if needed. |  |
| Prevention | Schedule has actor-free blocks (6, 9) as rest. Craft services protein/sugar. Director briefs: "Trust me with energy." |  |

Risk 4.3 — Actor Injury on Set

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | LOW |  |
| Impact | HIGH |  |
| Description | Trip on rug, bump furniture, cut on prop daggers. |  |
| Contingency | First aid kit on set. Treat minor injuries if willing. Significant = wrap day. |  |
| Prevention | Tape rug edges. Mark track/cables with glow tape. Bladed props out of reach. Crew briefing. |  |

CATEGORY 5: Location & Environment Risks

Risk 5.1 — Power Outage

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | LOW–MEDIUM | Area reliability |
| Impact | HIGH |  |
| Description | Power stability unreliable in rural areas. |  |
| Contingency | Portable generator or battery station backup for camera, recorder, monitor. |  |
| Prevention | Ask property owner about reliability. Schedule during stable hours. Consider silent generator insurance. |  |

Risk 5.2 — Unexpected Exterior Noise

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | MEDIUM | Rural location |
| Impact | MEDIUM | Dialogue shots affected |
| Description | Construction, aircraft, prayer calls, animals. |  |
| Contingency | Hold for sound. Mixer calls HOLD or SOUND NOTE. AD decides: wait or plan ADR. Prayer calls are predictable. |  |
| Prevention | Visit at SAME TIME OF DAY. Listen 15 min. Note patterns. Ask owner about construction, dogs, mosque. |  |

Risk 5.3 — Location Access Denied Day-Of

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | LOW | If properly arranged |
| Impact | CRITICAL | No location = no shoot |
| Description | Property owner changes mind, gate locked, access road blocked. |  |
| Contingency | NO same-day fix. Shoot postponed. PM contacts owner to resolve. |  |
| Prevention | Written agreement with owner: dates, hours, crew size, property use. Confirm 48 hrs + evening before. |  |

CATEGORY 6: Data & Footage Risks

Risk 6.1 — Card / Data Loss

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | LOW |  |
| Impact | CATASTROPHIC | Lost footage = lost day |
| Description | Card corruption, accidental deletion, physical damage. |  |
| Contingency | Dual card recording if supported. Swap at breaks, offload completed card. |  |
| Prevention | NEVER format until backed up to TWO drives. Reputable brands. Never remove while writing. Label and log. |  |

Risk 6.2 — Audio / Video Sync Issues

| Field | Detail | Impact |
| --- | --- | --- |
| Likelihood | LOW–MEDIUM |  |
| Impact | MEDIUM | Fixable in post, costs time |
| Description | Timecode not synced. Manual sync needed in post. |  |
| Contingency | If clapper missed, actor CLAPS visibly on camera. Auto-sync software (PluralEyes, DaVinci). |  |
| Prevention | Jam timecode camera/recorder at start and each break. Slate every take (2nd AC responsible). |  |

Master Risk Register

| # | Risk | Likelihood | Impact | Mitigation Summary |
| --- | --- | --- | --- | --- |
| 1.1 | Tracking shot overrun | HIGH | HIGH | Cap 8 takes, split if needed |
| 1.2 | Dialogue run long | MEDIUM | MEDIUM | Sacrifice Shot 12.2 |
| 1.3 | Director wants more | MEDIUM | MEDIUM–HIGH | Present trade-offs |
| 2.1 | Dolly/track failure | LOW | HIGH | Steadicam/handheld/slider |
| 2.2 | Camera/lens failure | LOW | CRITICAL | Backup body + lenses |
| 2.3 | Lighting failure | LOW–MEDIUM | MEDIUM | Spare bulbs, rearrange |
| 2.4 | Sound equipment fail | LOW | HIGH | Scratch audio, fix before dialogue |
| 3.1 | Deer head unavailable | MEDIUM | HIGH | Painting/photo or substitute |
| 3.2 | Deer head falls | LOW | CRITICAL | Safety wire, test mount |
| 3.3 | Lock unconvincing | MEDIUM | MEDIUM | Install bolt or wedge |
| 4.1 | Actors not cast | MEDIUM | CRITICAL | 1-week deadline |
| 4.2 | Actor fatigue | MEDIUM | MEDIUM–HIGH | Rest blocks, break before Block 10 |
| 4.3 | Actor injury | LOW | HIGH | First aid, wrap if significant |
| 5.1 | Power outage | LOW–MEDIUM | HIGH | Generator/battery |
| 5.2 | Exterior noise | MEDIUM | MEDIUM | Hold for sound, plan around calls |
| 5.3 | Access denied | LOW | CRITICAL | Written agreement, confirm twice |
| 6.1 | Card loss | LOW | CATASTROPHIC | Dual recording, dual backup |
| 6.2 | Sync issues | LOW–MEDIUM | MEDIUM | Timecode jam, hand clap backup |

Document Status: LOCKED v1.0 — April 2026