SHOOTING SCHEDULE / STRIPBOARD — Scene 12

Film: Mysterious Guest (میوانێکی نادیار)

Director: Sarwar Muhedin

Scene: 12 — INT. Garden House — Evening

Shoot Date: [TBD]

Call Time: [TBD — recommend 10:00 AM for a 5-hour interior day]

Wrap Estimate: [TBD — approx. 5 hours after first take]

Location: Garden House Interior [Address TBD]

Stripboard

Each strip represents one shooting block.

Color coding:

- YELLOW = dialogue,

- WHITE = silent/visual,

- BLUE = insert/no actors.

- Read top to bottom = shooting order for the day.

PRE-CALL: Set Dressing & Lighting (60 min before first take)

| Time Offset | Task | Who |
| --- | --- | --- |
| -60 min | Crew call. Unload equipment, set up video village. | All crew |
| -60 min | Begin set dressing: mount deer head, hang masks, place daggers/sword, dress desk with laptop + papers, position sculptures on shelves. | Art dept / Props |
| -45 min | Position practical lights (pendant lamps, shelf lights, desk lamp). Set dimmers. | Gaffer + Grip |
| -30 min | Lay dolly track for Setup A (entrance to mid-room, ~3m). | Grip |
| -20 min | Actors arrive. Wardrobe + makeup check. | Cast, Wardrobe, Makeup |
| -15 min | Blocking rehearsal for Shot 12.1 (tracking shot) — walk-through with actors on track, no camera. | Director, Cast, DP |
| -5 min | Final checks: frame, focus marks, sound levels, slate info. | DP, Sound, AC |

BLOCK 1 — THE TRACKING SHOT

| Field | Detail |
| --- | --- |
| Time | 0:00 – 0:45 |
| Duration | 45 min |
| Setup | A |
| Shot | 12.1 |
| Type | YELLOW (action + blocking, no dialogue) |
| Cast Required | Nali, Gesha |
| Description | Tracking shot from entrance into the room. Camera follows Nali and Gesha through doorway, pans to stay with Gesha as she freezes. |
| Equipment | Dolly + track (3m), 24mm lens |
| Est. Takes | 5–8 |
| Turnaround | Strike dolly track after this block. Reset to tripod for Block 2. |
| Notes | Shoot while energy is highest. Each reset requires both actors back outside the door. Budget 4 min per take cycle (action + reset + notes). |

BLOCK 2 — DINING TABLE DIALOGUE + REACTION

| Field | Detail |
| --- | --- |
| Time | 0:45 – 1:20 |
| Duration | 35 min |
| Setup | F → C |
| Shots | 12.6, then 12.3 |
| Type | YELLOW (dialogue) then WHITE (reaction) |
| Cast Required | Nali + Gesha (12.6), Gesha only (12.3) |
| Description | Two shot dialogue at dining table (12.6: "Why didn't you tell me..."), then tighten to Gesha's close-up reaction (12.3). |
| Equipment | Tripod, 40mm → swap to 85mm |
| Est. Takes | 4–6 (12.6), 3–4 (12.3) |
| Turnaround | Lens swap only between shots. Move camera base to kitchen area for Block 3. |
| Notes | Release Nali after 12.6 if needed — 12.3 is Gesha only. |

BLOCK 3 — NALI WATCHES (KITCHEN OTS)

| Field | Detail |
| --- | --- |
| Time | 1:20 – 1:30 |
| Duration | 10 min |
| Setup | D |
| Shot | 12.4 |
| Type | WHITE (no dialogue) |
| Cast Required | Nali (foreground), Gesha (background action) |
| Description | Over Nali's shoulder from kitchen counter. He watches Gesha explore. |
| Equipment | Tripod, 50mm |
| Est. Takes | 2–3 |
| Turnaround | Move camera to opposite side of room for Block 4. |
| Notes | Quick setup. Gesha doesn't need to perform specific action — just be in background exploring naturally. |

☕ BREAK 1 (15 min) — 1:30 – 1:45

Crew reset. Actors rest. Move camera base to west side for Nali's coverage.

BLOCK 4 — NALI'S DIALOGUE COVERAGE

| Field | Detail |
| --- | --- |
| Time | 1:45 – 2:00 |
| Duration | 15 min |
| Setup | I |
| Shots | 12.10, then 12.12 |
| Type | YELLOW (dialogue) |
| Cast Required | Nali only (Gesha off-screen for eyeline if available) |
| Description | Nali medium shot answering mask questions (12.10), then tighten to close-up for "Yes, it's the title of my new play" (12.12). |
| Equipment | Tripod, 50mm → swap to 85mm |
| Est. Takes | 3–4 each |
| Turnaround | Lens swap only. Same camera position for both. Move to west wall for Block 5. |
| Notes | Gesha can stand off-camera for Nali's eyeline, or use a mark. Back-to-back same axis = efficient. |

BLOCK 5 — MASK DISCOVERY (3 SHOTS)

| Field | Detail |
| --- | --- |
| Time | 2:00 – 2:20 |
| Duration | 20 min |
| Setup | G → G (tighter) → H |
| Shots | 12.7, 12.9, then 12.8 |
| Type | WHITE (12.7), YELLOW (12.9), BLUE (12.8 insert) |
| Cast Required | Gesha (12.7, 12.9), No actors (12.8) |
| Description | Gesha approaches masks (12.7), questions about masks tighter (12.9), then mask insert close-up (12.8). |
| Equipment | Tripod, 50mm (12.7, 12.9) → reposition + swap to 85mm macro (12.8) |
| Est. Takes | 3 + 3–4 + 2–3 |
| Turnaround | Small reposition between 12.9 and 12.8. Release Gesha after 12.9 for break if needed. |
| Notes | Pre-light the masks BEFORE this block — the dim practical behind the bookshelf must be set during Break 1. 12.8 can be shot without actors — schedule flexibility. |

BLOCK 6 — DEER HEAD POV

| Field | Detail |
| --- | --- |
| Time | 2:20 – 2:35 |
| Duration | 15 min |
| Setup | E |
| Shot | 12.5 |
| Type | WHITE (no actors, no dialogue) |
| Cast Required | None |
| Description | Gesha's POV — slow push toward deer head. Subjective camera. |
| Equipment | Slider (1m minimum), 35mm |
| Est. Takes | 3–4 |
| Turnaround | Strike slider. Set up for desk area (Block 7). |
| Notes | No actors needed — this is camera + lighting only. Focus on the eye-glint in the deer head's glass eye. Can use this block to give actors rest time. |

BLOCK 7 — DESK DISCOVERY

| Field | Detail |
| --- | --- |
| Time | 2:35 – 2:50 |
| Duration | 15 min |
| Setup | J (+J2 insert) |
| Shots | 12.11, plus paper insert |
| Type | YELLOW (dialogue) + BLUE (insert) |
| Cast Required | Gesha (12.11), None (insert) |
| Description | Gesha at desk finds "Stories are waiting" paper (12.11). Cutaway insert of paper close-up (J2). |
| Equipment | Dolly or slider for slight track (12.11: 40mm), tripod for insert (85mm) |
| Est. Takes | 3–4 + 2 (insert) |
| Turnaround | Move camera to center-right for Block 8. |
| Notes | Shoot the paper insert after Gesha's coverage — doesn't need actress. Confirm paper prop is ready: handwritten "Stories are waiting" in dark ink on cream paper. |

☕ BREAK 2 (15 min) — 2:50 – 3:05

Crew reset. Review footage from Blocks 1–7 on monitor if time permits. Prepare for final three blocks — these are the emotional climax of the scene.

BLOCK 8 — GESHA RETURNS TO DEER

| Field | Detail |
| --- | --- |
| Time | 3:05 – 3:20 |
| Duration | 15 min |
| Setup | K |
| Shot | 12.13 |
| Type | YELLOW (dialogue) |
| Cast Required | Gesha (on camera), Nali (off-screen voice) |
| Description | Gesha walks back to deer head, calmer now. Dialogue about the sculptures. She chooses the deer. |
| Equipment | Tripod with fluid head (pan), 50mm |
| Est. Takes | 3–4 |
| Turnaround | Move camera to center-left for Block 9. |
| Notes | Nali delivers his off-screen lines from behind camera. If Nali is unavailable, director can read lines. But having Nali present gives Gesha a real voice to react to. |

BLOCK 9 — ROOM REVEAL (NO ACTORS)

| Field | Detail |
| --- | --- |
| Time | 3:20 – 3:30 |
| Duration | 10 min |
| Setup | B |
| Shot | 12.2 |
| Type | BLUE (no actors) |
| Cast Required | None |
| Description | Low angle wide shot of the full room interior. The room as a character. |
| Equipment | Hi-hat or low tripod on floor, 18mm ultra-wide |
| Est. Takes | 2–3 |
| Turnaround | Reset to center-left for Block 10. |
| Notes | All practicals must be ON. Check frame edges for modern items (water bottles, phone chargers, crew bags). Clear the room of people. This shot can also be used as a safety — if any insert shots were missed, grab them in this window. |

BLOCK 10 — THE LOCKED DOOR

| Field | Detail |
| --- | --- |
| Time | 3:30 – 3:50 |
| Duration | 20 min |
| Setup | L |
| Shot | 12.14 |
| Type | YELLOW (dialogue + critical performance) |
| Cast Required | Gesha (foreground), Nali (background) |
| Description | Wide shot — Gesha tries locked door, Nali redirects her, she enters his room. THE SEED SHOT. |
| Equipment | Tripod (or dolly for micro-move), 28mm |
| Est. Takes | 4–6 |
| Turnaround | Move camera to entrance area for Block 11. |
| Notes | Director should speak to Gesha privately before this block: "The look you give Nali is the whole shot. You want to ask why the door is locked. You decide not to. It's not fear — it's politeness. You're a guest." Capture the SOUND of the locked door handle — metal resistance. Sound dept: isolate this for post. |

BLOCK 11 — NALI ALONE (FINAL SHOT)

| Field | Detail |
| --- | --- |
| Time | 3:50 – 4:00 |
| Duration | 10 min |
| Setup | M |
| Shot | 12.15 |
| Type | WHITE (no dialogue) |
| Cast Required | Nali only |
| Description | Nali stands alone. Picks up phone, grabs meat for dog, exits. Hold on empty room. |
| Equipment | Tripod, 50mm |
| Est. Takes | 2–3 |
| Turnaround | — (final shot of the day) |
| Notes | SHOOT LAST. This is the emotional button. Release Gesha before this block — Nali is alone. After Nali exits frame, hold the static empty room for at LEAST 5 seconds. The editor will decide how long to keep it, but give them the footage. This is where the scene lives or dies. |

Day Summary

| Metric | Value |
| --- | --- |
| First Take | 0:00 |
| Last Take | ~4:00 |
| Total Active Shooting | 3 hrs 30 min |
| Breaks | 2 × 15 min = 30 min |
| Pre-call (setup/dressing) | 60 min |
| Buffer | 30 min |
| **Total Day (call to wrap)** | **~5 hrs 30 min** |

Cast Day Breakdown

| Actor | Call Time Offset | First Shot | Last Shot | Wrap Estimate | On-Set Hours |
| --- | --- | --- | --- | --- | --- |
| **Nali** | -20 min (wardrobe/makeup) | 12.1 (Block 1) | 12.15 (Block 11) | End of day | ~4 hrs 30 min |
| **Gesha** | -20 min (wardrobe/makeup) | 12.1 (Block 1) | 12.14 (Block 10) | After Block 10 | ~4 hrs 10 min |

**Gesha release:** After Block 10 (Shot 12.14). She is not needed for Block 11 (Nali alone).

**Nali gaps:** Nali is not on camera in Blocks 5 (mask insert), 6 (deer POV), 7 (desk — Gesha only + insert), and 9 (room reveal). He can rest during these blocks but should remain on set for off-screen eyeline and voice in Block 8.

Contingency Notes

| Risk | Mitigation |
| --- | --- |
| Tracking shot (12.1) takes too long | Cap at 8 takes. If no clean take by take 8, consider splitting into two shots (entrance wide + Gesha reaction) and combining in edit. |
| Actor fatigue on dialogue shots | Schedule intensive performance shots (Blocks 2, 10) with rest blocks between them (Blocks 6, 9 have no actors). |
| Equipment failure (dolly/slider) | Shots 12.1 and 12.5 can be done handheld as fallback. 12.11 tracking can become static. Quality changes but coverage is preserved. |
| Lighting consistency across blocks | Photograph the lighting setup after Block 1 for reference. All practicals should be on dimmers — label each dimmer position. |
| Time overrun | Block 9 (room reveal, 12.2) is the sacrificial shot — it can be cut or reduced to 1 take if time is tight. It's beautiful but not story-critical. |
| Props not ready | Deer head and masks are critical — everything else can be improvised. Have backup plan for deer head (large framed photograph of a deer as last resort). |

Document Status: LOCKED v1.0 — April 2026